## Estimate (hidden)
E S T I M A T E
NAME OF WORK:- |  | ADDITION BLOCK & IMPROVEMENT OF GOVERNMENT GIRLS COLLEGE BLOCK # 16, F.B.AREA, GULBERG TOWN, KARACHI.(ADP # 185).
S.No: | Description of Item | [12 empty] | Qty
1 | Excavation in foundation of building bridges and other structure I/c degabilling dressing refilling, around structure with excavated earth waterig and ramming lead upto 5 ft in ordinary soil (S.I.No:18-b/P-5).
Footing (Academic Block).
| Footing-1 | 1 | x | 6 | x | 9 | x | 9 | x | 5 |  |  |  | = | 2430
| Footing-2 | 1 | x | 9 | x | 8.5 | x | 8.5 | x | 5 |  |  |  | = | 3251.25
| Footing-3 | 1 | x | 11 | x | 8 | x | 8 | x | 5 |  |  |  | = | 3520
| Footing-4 | 1 | x | 5 | x | 6 | x | 6 | x | 5 |  |  |  | = | 900
| Footing-5 | 1 | x | 17 | x | 5 | x | 5 | x | 5 |  |  |  | = | 2125
| Footing-6 | 1 | x | 4 | x | 13 | x | 13 | x | 5 |  |  |  | = | 3380
| Footing-7 | 1 | x | 6 | x | 7 | x | 7 | x | 5 |  |  |  | = | 1470
| CF-1 | 1 | x | 1 | x | 40.5 | x | 7 | x | 5 |  |  |  | = | 1417.5
| CF-1 | 1 | x | 1 | x | 87 | x | 7 | x | 5 |  |  |  | = | 3045
[13 empty] | A |  | 21538.75
Footing (Labs.+ Admin: Block).
| Footing-1 | 1 | x | 7 | x | 10 | x | 10 | x | 5 |  |  |  | = | 3500
| Footing-2 | 1 | x | 31 | x | 9.5 | x | 9.5 | x | 5 |  |  |  | = | 13988.75
| Footing-3 | 1 | x | 45 | x | 9 | x | 9 | x | 5 |  |  |  | = | 18225
| Footing-4 | 1 | x | 10 | x | 8 | x | 8 | x | 5 |  |  |  | = | 3200
| Footing-5 | 1 | x | 37 | x | 7 | x | 7 | x | 5 |  |  |  | = | 9065
[13 empty] | B |  | 47978.75
Outer outer Perimeter walls
| End wall S/Wall | 1 | x | 34 | x | 2 | x | 2 | [5 empty] | = | 136
| B/side L/W C/R | 1 | x | 235.67 | x | 2 | x | 2 | [5 empty] | = | 942.68
| Canteen Walls | 1 | x | 31.33 | x | 2 | x | 2 | [5 empty] | = | 125.32
| Canteen Walls | 1 | x | 42 | x | 2 | x | 2 | [5 empty] | = | 168
| Canteen Walls | 1 | x | 16.33 | x | 2 | x | 2 | [5 empty] | = | 65.32
| Canteen Walls | 1 | x | 10.67 | x | 2 | x | 2 | [5 empty] | = | 42.68
| Canteen Walls | 1 | x | 16 | x | 2 | x | 2 | [5 empty] | = | 64
| Canteen Walls | 1 | x | 30.67 | x | 2 | x | 2 | [5 empty] | = | 122.68
| R/S of lobby | 1 | x | 31 | x | 2 | x | 2 | [5 empty] | = | 124
| B/S of labs | 1 | x | 139 | x | 2 | x | 2 | [5 empty] | = | 556
| B/S of labs | 1 | x | 167.33 | x | 2 | x | 2 | [5 empty] | = | 669.32
| S/W of commn Room | 1 | x | 39 | x | 2 | x | 2 | [5 empty] | = | 156
| F/S of Labs | 1 | x | 129 | x | 2 | x | 2 | [5 empty] | = | 516
| F/S of Labs | 1 | x | 80 | x | 2 | x | 2 | [5 empty] | = | 320
| Side walls of Admin | 1 | x | 85.5 | x | 2 | x | 2 | [5 empty] | = | 342
| Side walls of Admin | 1 | x | 67.33 | x | 2 | x | 2 | [5 empty] | = | 269.32
| Side walls of Admin | 1 | x | 85.5 | x | 2 | x | 2 | [5 empty] | = | 342
| F/S of lobby | 1 | x | 46 | x | 2 | x | 2 | [5 empty] | = | 184
| F/S of lobby | 1 | x | 164 | x | 2 | x | 2 | [5 empty] | = | 656
[13 empty] | C |  | 5801.32
Stair Case
| S/C Base | 1 | x | 2 | x | 10 | x | 5 | x | 3 |  |  |  | = | 300
[13 empty] | D |  | 300
Under Ground Tank
| U.G.Tank | 1 | x | 30 | x | 20 | x | 7 | [5 empty] | = | 4200
[13 empty] | E |  | 4200
Compound Wall
| C/Wall | 1 | x | 1600 | x | 2.5 | x | 3 | [5 empty] | = | 12000
[13 empty] | F |  | 12000
Guard Room
| Footing | 2 | x | 4 | x | 6 | x | 6 | x | 5 |  |  |  | = | 1440
| Lav: Footing | 1 | x | 4 | x | 4 | x | 4 | x | 5 |  |  |  | = | 320
[13 empty] | G |  | 1760
Main Gate Pillers
| Main Gate Pillers | 1 | x | 4 | x | 7 | x | 7 | x | 5 |  |  |  | = | 980
[13 empty] | H |  | 980
| G.Total | A + B + C + D + E + F + G + H | [11 empty] | = | 94558.82
2 | Cement concrete brick or stone ballast 1 1/2" to 2" guage ratio 1:4:8 (S.I.No:4-b/P-17).
| Qnty: same as item No.1-A |  | 21538.75 |  | x | 0.5 | / | 5 | [5 empty] | = | 2154
| Qnty: same as item No.1-B |  | 47978.75 |  | x | 0.5 | / | 5 | [5 empty] | = | 4798
| Qnty: same as item No.1-C |  | 5801.32 |  | x | 0.33 | / | 2 | [5 empty] | = | 957
| Qnty: same as item No.1-D |  | 300 |  | x | 0.5 | / | 3 | [5 empty] | = | 50
| Qnty: same as item No.1-E |  | 4200 |  | x | 0.5 | / | 7 | [5 empty] | = | 300
| Qnty: same as item No.1-F |  | 12000 |  | x | 0.5 | / | 3 | [5 empty] | = | 2000
| Qnty: same as item No.1-G |  | 1760 |  | x | 0.5 | / | 5 | [5 empty] | = | 176
| Qnty: same as item No.1-H |  | 980 |  | x | 0.5 | / | 5 | [5 empty] | = | 98
[13 empty] | A |  | 10533
Under Bed
| Lav: Block | 1 | x | 10 | x | 25 | x | 0.42 | [5 empty] | = | 105
| C/Rooms | 5 | x | 30 | x | 25 | x | 0.42 | [5 empty] | = | 1575
| Ver: | 1 | x | 164 | x | 7 | x | 0.42 | [5 empty] | = | 482.16
| Lobby | 1 | x | 71 | x | 69 | x | 0.42 | [5 empty] | = | 2057.58
| Canteen / Kit: | 1 | x | 30 | x | 30 | x | 0.42 | [5 empty] | = | 378
| Canteen / Kit: | 1 | x | 10 | x | 15 | x | 0.42 | [5 empty] | = | 63
| Labs | 1 | x | 139 | x | 39 | x | 0.42 | [5 empty] | = | 2276.82
| Labs | 1 | x | 129 | x | 39 | x | 0.42 | [5 empty] | = | 2113.02
| Admin: Block | 1 | x | 85.5 | x | 67 | x | 0.42 | [5 empty] | = | 2405.97
| Guard Rooms | 2 | x | 14 | x | 14 | x | 0.42 | [5 empty] | = | 164.64
[13 empty] | B |  | 11621.19
[6 empty] | Total:- |  | A | + | B |  |  |  | = | 22154.19
3 | P/L 1:3:6 c.c solid block masonary set in 1:6 cement sand mortor in plinth and foundation I/c raking out joints and curing etc complete.(S.I.No: 21/P-22).
| Qnty: same as item No.1-C | ( | 5801.32 |  | x | 0.67 | x | 2.5 | ) / | 2 | x | 2 |  | = | 9717
| C/Wall Ist Step | 1 | x | 1600 | x | 1.5 | x | 1.5 | [5 empty] | = | 3600
| Admin: Block | 1 | x | 1600 | x | 1 | x | 2 | [5 empty] | = | 3200
| Admin: Block | 2 | x | 4 | x | 13 | x | 0.67 | x | 2.5 |  |  |  | = | 174
| Admin: Block | 1 | x | 32 | x | 2 | x | 2.5 | [5 empty] | = | 160
16851
4 | Filling watering and ramming surplus earth in from foundation lead upto one chain and lift upto 5 feet. (S.I.No.21 P-5).
| Qnty: same as item No.1 | 94558.82 |  |  | / | 3 | [7 empty] | = | 31519.6067
5 | Filling watering and ramming New earth in floor with from out side lead upto one chain and lift upto 5 feet. (S.I.No.22 P-5).
| Qnty: same as item No.2-B | 11621.19 |  |  | x | 2.5 | / | 0.42 | [5 empty] | = | 69173.75
Deduction
| Qnty: same as item No.4 | 31519.6067 | [11 empty] | = | 31519.6067
| Net Qnty: |  |  |  | 69173.75 |  |  | - | 31519.6067 |  |  |  |  | = | 37654.1433
6 | R.C.C work 1:2:4 in/c all labour & material except the cost of steel R/F & bending & binding which will be paid seprately. R.C.C work roof slab beams coloumns rafts lentel and other structure member laid in situ or pre cast laid in posiion complete in all respect ratio 1:2:4.(S.I.No.6/a-i/P-19)
(Academic Block).
| Footing -1 | 1 | x | 6 | x | 8 | x | 8 | x | 2 |  |  |  | = | 768
| Footing -2 | 1 | x | 9 | x | 7.5 | x | 7.5 | x | 2 |  |  |  | = | 1013
| Footing -3 | 1 | x | 11 | x | 7 | x | 7 | x | 2 |  |  |  | = | 1078
| Footing -4 | 1 | x | 5 | x | 5 | x | 5 | x | 1.75 |  |  |  | = | 219
| Footing -5 | 1 | x | 17 | x | 4 | x | 4 | x | 2 |  |  |  | = | 544
| Footing -6 | 1 | x | 4 | x | 12 | x | 12 | x | 2 |  |  |  | = | 1152
| Footing -7 | 1 | x | 6 | x | 6 | x | 6 | x | 1.75 |  |  |  | = | 378
| C- Footing -1 | 1 | x | 1 | x | 40 | x | 6 | x | 2 |  |  |  | = | 480
| C- Footing -1 | 1 | x | 1 | x | 86 | x | 6 | x | 2 |  |  |  | = | 1032
[13 empty] | A |  | 6664
Column Below Plinth
| Col-1 | 1 | x | 40 | x | 0.92 | x | 2.25 | x | 3.5 |  |  |  | = | 290
| Col-2 | 1 | x | 18 | x | 0.75 | x | 1.25 | x | 3.5 |  |  |  | = | 59
| Col-3 | 1 | x | 4 | x | 2.25 | x | 2.25 | x | 3.5 |  |  |  | = | 71
| Col-4 | 1 | x | 6 | x | 1.25 | x | 2.25 | x | 3.5 |  |  |  | = | 59
| Col-5 | 1 | x | 2 | x | 1.75 | x | 2.25 | x | 3.5 |  |  |  | = | 28
| Col-6 | 1 | x | 3 | x | 1.75 | x | 1.75 | x | 3.5 |  |  |  | = | 32
[13 empty] | B |  | 539
Labs + Admin Block
| Footing -1 | 1 | x | 7 | x | 9 | x | 9 | x | 1.75 |  |  |  | = | 992
| Footing -2 | 1 | x | 31 | x | 8.5 | x | 8.5 | x | 1.75 |  |  |  | = | 3920
| Footing -3 | 1 | x | 45 | x | 8 | x | 8 | x | 1.75 |  |  |  | = | 5040
| Footing -4 | 1 | x | 10 | x | 7 | x | 7 | x | 1.75 |  |  |  | = | 858
| Footing -5 | 1 | x | 37 | x | 6 | x | 6 | x | 1.5 |  |  |  | = | 1998
[13 empty] | C |  | 12808
Column Below Plinth
| Col-1 | 1 | x | 71 | x | 0.92 | x | 2.25 | x | 3.75 |  |  |  | = | 551
| Col-2 | 1 | x | 36 | x | 1.25 | x | 1.25 | x | 3.75 |  |  |  | = | 211
| Col-3 | 1 | x | 22 | x | 1 | x | 2.5 | x | 3.75 |  |  |  | = | 206
[13 empty] | D |  | 968
Guard Room Footins
| Footing | 1 | x | 2 | x | 4 | x | 5 | x | 1.25 |  |  |  | = | 50
| Lav: | 1 | x | 4 | x | 3 | x | 3 | x | 1 |  |  |  | = | 36
| M.Gate | 1 | x | 4 | x | 6 | x | 6 | x | 1.75 |  |  |  | = | 252
[13 empty] | E |  | 338
Coloumn Below Plinth
| G.Lav: | 2 | x | 4 | x | 0.92 | x | 2.25 | x | 4 |  |  |  | = | 66
| Lav: | 1 | x | 4 | x | 0.92 | x | 2.25 | x | 4.25 |  |  |  | = | 35
| M.Gate | 1 | x | 4 | x | 2.25 | x | 2.25 | x | 3.75 |  |  |  | = | 76
[13 empty] | F |  | 177
Plinth Beams (Acad:+Adimin+Labs)
| Qnty same as Item No.1-C | ( | 5801.32 |  | x | 0.67 | x | 2 | )/( | 2 | x | 2 | ) | = | 1943
| FB-2 Grid (20) | 1 | x | 80 | x | 1 | x | 5.5 | [5 empty] | = | 440
| FB- Grid (19) | 1 | x | 66.5 | x | 1 | x | 5.5 | [6 empty] | 366
| PB 4 Grid (N) | 1 | x | 44 | x | 0.67 | x | 2.5 | [6 empty] | 74
| PB-2 grid 2 to 10 | 5 | x | 25 | x | 0.67 | x | 2.5 | [5 empty] | = | 209
| PB-1 grid 'H' | 1 | x | 164 | x | 0.67 | x | 2 | [5 empty] | = | 220
| FB-1,2 Grid 12,13 | 2 | x | 34 | x | 1 | x | 5.5 | [5 empty] | = | 374
[13 empty] | G |  | 3626
| P.B-4 Grid 14,17 | 1 | x | 2 | x | 66.5 | x | 0.67 | x | 2.5 |  |  |  | = | 223
| P.B-4 grid G,K | 1 | x | 2 | x | 71 | x | 0.67 | x | 2.5 |  |  |  | = | 238
[13 empty] | H |  | 461
| PB- grid X | 2 | x | 10 | x | 0.67 | x | 2 | [5 empty] | = | 27
| PB-1 grid w | 1 | x | 140 | x | 0.67 | x | 2 | [5 empty] | = | 188
| PB- grid V | 1 | x | 30 | x | 0.67 | x | 2 | [5 empty] | = | 40
| PB-1 grid u | 1 | x | 67 | x | 0.67 | x | 2 | [5 empty] | = | 90
| PB-1 grid R,O, H | 3 | x | 18 | x | 0.67 | x | 2 | [5 empty] | = | 72
| PB-1 grid M,K,H | 3 | x | 30 | x | 0.67 | x | 2 | [5 empty] | = | 121
| PB-1 grid L,N,D,C | 4 | x | 30 | x | 0.67 | x | 2 | [5 empty] | = | 161
| PB-1 grid 9,10,13,15,18 | 5 | x | 30 | x | 0.67 | x | 2 | [5 empty] | = | 201
| PB-1 grid 16 | 1 | x | 129 | x | 0.67 | x | 2 | [5 empty] | = | 173
| P.B grid 6,3,2 | 3 | x | 85 | x | 0.67 | x | 2 | [5 empty] | = | 342
| PB-1 grid 4 | 1 | x | 44 | x | 0.67 | x | 2 | [5 empty] | = | 59
| For P/Walls | 1 | x | 18 | x | 0.67 | x | 2 | [5 empty] | = | 24
| For P/Walls | 1 | x | 16 | x | 0.67 | x | 2 | [5 empty] | = | 21
| For P/Walls | 1 | x | 6 | x | 0.67 | x | 2 | [5 empty] | = | 8
| For P/Walls | 1 | x | 13.33 | x | 0.67 | x | 2 | [5 empty] | = | 18
| For P/Walls | 2 | x | 10 | x | 0.67 | x | 2 | [5 empty] | = | 27
| For P/Lav: | 1 | x | 25 | x | 0.67 | x | 2 | [5 empty] | = | 34
| For P/Lav: | 4 | x | 5 | x | 0.67 | x | 2 | [5 empty] | = | 27
| For P/Lav: | 1 | x | 30 | x | 0.67 | x | 2 | [5 empty] | = | 40
| For P/Lav: | 5 | x | 5 | x | 0.67 | x | 2 | [5 empty] | = | 34
[13 empty] | I |  | 1707
Guard Room
| P.Beam | 2 | x | 4 | x | 14 | x | 0.67 | x | 2 |  |  |  | = | 150
| Lav: | 1 | x | 4 | x | 8 | x | 0.67 | x | 2.5 |  |  |  | = | 54
[13 empty] | J |  | 204
| M.Gate | 1 | x | 32 | x | 2 | x | 2 |  |  |  |  | K | = | 128
S.S Coloumns (Academic)
| G.F C-1 | 1 | x | 40 | x | 0.67 | x | 2 | x | 8.25 |  |  |  | = | 442
| G.F C-2 | 1 | x | 18 | x | 0.5 | x | 1 | x | 10.25 |  |  |  | = | 92
| G.F C-3 | 1 | x | 4 | x | 2 | x | 2 | x | 10.25 |  |  |  | = | 164
| G.F C-4 | 1 | x | 6 | x | 1 | x | 2 | x | 8.25 |  |  |  | = | 99
| G.F C-5 | 1 | x | 2 | x | 1.5 | x | 2 | x | 8.25 |  |  |  | = | 50
| G.F C-6 | 1 | x | 3 | x | 1.5 | x | 1.5 | x | 8.25 |  |  |  | = | 56
[13 empty] | L |  | 903
Labs + Admin
| G.F C-1 | 1 | x | 71 | x | 0.67 | x | 2 | x | 8.25 |  |  |  | = | 785
| G.F C-2 | 1 | x | 36 | x | 1 | x | 1 | x | 10.25 |  |  |  | = | 369
| G.F C-3 | 1 | x | 22 | x | 1 | x | 2.25 | x | 8.25 |  |  |  | = | 408
[13 empty] | M |  | 1562
F.F S.S Coloumns (Academic)
| Qnty same as itme No. 6 (L) |  | 903 | [9 empty] | N | = | 903
F.F S.S Coloumns (Labs+Admin)
| C-1 | 1 | x | 38 | x | 0.67 | x | 2 | x | 8.25 |  |  |  | = | 420
| C-2 | 1 | x | 22 | x | 1 | x | 1 | x | 10.25 |  |  |  | = | 226
| C-3 | 1 | x | 18 | x | 1 | x | 2.25 | x | 8.25 |  |  |  | = | 334
[13 empty] | O |  | 980
Tower Coloumns
| Twoer Coloumns | 1 | x | 4 | x | 2 | x | 2 | x | 7.17 |  |  |  | = | 115
| M.Gate Coloumn | 1 | x | 4 | x | 2 | x | 2 | x | 14 |  |  |  | = | 224
| Guard Room | 2 | x | 4 | x | 0.67 | x | 2 | x | 7.25 |  |  |  | = | 78
| Lav: | 1 | x | 4 | x | 0.5 | x | 1 | x | 7.25 |  |  |  | = | 15
[13 empty] | P |  | 432
Beam Below Slab
| Qnty same as Item No.1-C | ( | 5801.32 |  | x | 0.67 | x | 4 | )/( | 2 | x | 2 | ) | = | 3887
| Beam grid 20 | 1 | x | 80 | x | 0.67 | x | 3 | [5 empty] | = | 161
| Beam grid (19) | 1 | x | 66.5 | x | 0.67 | x | 3 | [5 empty] | = | 134
| Bean grid 'N' | 1 | x | 44 | x | 0.67 | x | 3 | [5 empty] | = | 88
| Beam grid 2 to 10 | 5 | x | 25 | x | 0.67 | x | 3 | [5 empty] | = | 251
| Beam grid 'H' | 1 | x | 164 | x | 0.67 | x | 3 | [5 empty] | = | 330
| Beam grid 12 , 13 | 2 | x | 34 | x | 0.67 | x | 3 | [5 empty] | = | 137
| Lobby Beams | 2 | x | 66.5 | x | 1 | x | 2 | [5 empty] | = | 266
| Lobby Beams | 2 | x | 71 | x | 1 | x | 2 | [5 empty] | = | 284
| Qnty same as R.C.C -I |  | 1707 |  | x | 2 | / | 2 | [5 empty] | = | 1707
| Labs T-Beam | 4 | x | 2 | x | 30 | x | 1 | x | 2.5 |  |  |  | = | 600
| Statis lab:+Commn: Room | 1 | x | 2 | x | 30 | x | 1 | x | 2.5 |  |  |  | = | 150
| Librarty T-Beam | 1 | x | 2 | x | 30 | x | 1 | x | 2.5 |  |  |  | = | 150
| Staff T-Beam | 1 | x | 1 | x | 18 | x | 0.67 | x | 2 |  |  |  | = | 24
| C/Room T-Beams | 1 | x | 5 | x | 1 | x | 25 | x | 2 |  |  |  | = | 250
| Canteen T-Beams | 1 | x | 1 | x | 30 | x | 1 | x | 2.5 |  |  |  | = | 75
| Guard Rooms | 2 | x | 4 | x | 15.33 | x | 0.67 | x | 2 |  |  |  | = | 164
| Lav: | 1 | x | 4 | x | 8.33 | x | 0.67 | x | 2 |  |  |  | = | 45
| M/gate Beams | 1 | x | 1 | x | 32 | x | 1 | x | 4 |  |  |  | = | 128
| " Slab. | 1 | x | 32 | x | 9 | x | 0.5 | [5 empty] | = | 144
[13 empty] | Q |  | 8975
G.Floor Slab.
| c/Room wing | 1 | x | 167 | x | 34 | x | 0.5 | [5 empty] | = | 2839
| Lobby | 1 | x | 71 | x | 69 | x | 0.58 | [5 empty] | = | 2841
| canteen | 1 | x | 37.33 | x | 37.33 | x | 0.5 | [5 empty] | = | 697
| Kit | 1 | x | 13.67 | x | 22.33 | x | 0.5 | [5 empty] | = | 153
| Labs | 1 | x | 142 | x | 39 | x | 0.5 | [5 empty] | = | 2769
| Ver: Proj: | 1 | x | 80 | x | 3 | x | 0.5 | [5 empty] | = | 120
| Labs | 1 | x | 132 | x | 39 | x | 0.5 | [5 empty] | = | 2574
| Admin Block. | 1 | x | 88.5 | x | 73.33 | x | 0.5 | [5 empty] | = | 3245
| Loby: Projection | 1 | x | 46 | x | 8 | x | 0.67 | [5 empty] | = | 247
| Guard Room | 2 | x | 17.33 | x | 17.33 | x | 0.5 | [5 empty] | = | 300
| Lav: | 1 | x | 10.33 | x | 10.33 | x | 0.42 | [5 empty] | = | 45
[13 empty] | R |  | 15830
F.F Beams Below Slab
| C/R B/S H/W | 1 | x | 235.67 | x | 0.67 | x | 4 | [5 empty] | = | 632
| C/R B/S M/W | 1 | x | 164 | x | 0.67 | x | 4 | [5 empty] | = | 440
| C/R F/S Ver | 1 | x | 164 | x | 0.67 | x | 2 | [5 empty] | = | 220
| Lobby S/W | 1 | x | 70 | x | 0.67 | x | 2 | [5 empty] | = | 94
| Lobby S/W | 1 | x | 44.5 | x | 0.67 | x | 2 | [5 empty] | = | 60
| Lobby S/W | 1 | x | 46 | x | 0.67 | x | 2 | [5 empty] | = | 62
| Lob: Beam | 2 | x | 66.5 | x | 1 | x | 2 | [5 empty] | = | 266
| Lob: Beam | 2 | x | 71 | x | 1 | x | 2 | [5 empty] | = | 284
| C/R walls Beams | 6 | x | 25 | x | 0.67 | x | 2 | [5 empty] | = | 201
| Lav: end Beam | 1 | x | 34 | x | 0.67 | x | 2 | [5 empty] | = | 46
| C/R T-Beams | 5 | x | 25 | x | 1 | x | 2 | [5 empty] | = | 250
| Labs L/W | 2 | x | 2 | x | 102.67 | x | 0.67 | x | 4 |  |  |  | = | 1101
| Labs Lav: | 2 | x | 11.33 | x | 0.67 | x | 4 | [5 empty] | = | 61
| Labs F/S | 2 | x | 102.67 | x | 0.67 | x | 2 | [5 empty] | = | 275
| Lav: | 1 | x | 39 | x | 0.67 | x | 4 | [5 empty] | = | 105
| S/Walls | 2 | x | 5 | x | 30 | x | 0.67 | x | 2 |  |  |  | = | 402
| S/Walls | 2 | x | 2 | x | 10 | x | 0.67 | x | 2 |  |  |  | = | 54
| T- Beams | 8 | x | 30 | x | 1 | x | 2.5 | [5 empty] | = | 600
[13 empty] | S |  | 5153
F.Floor Slab
| C/R wings | 1 | x | 167 | x | 40 | x | 0.5 | [5 empty] | = | 3340
| Lobby | 1 | x | 71 | x | 69 | x | 0.5 | [5 empty] | = | 2450
| Labs | 1 | x | 105.67 | x | 42 | x | 0.5 | [5 empty] | = | 2219
| Lav: | 1 | x | 17.33 | x | 42 | x | 0.5 | [5 empty] | = | 364
| Ver: Proj: | 1 | x | 102.67 | x | 3 | x | 0.5 | [5 empty] | = | 154
| Labs: | 1 | x | 105.67 | x | 45 | x | 0.5 | [5 empty] | = | 2378
| Lobby Proj: | 1 | x | 46 | x | 8 | x | 0.58 | [5 empty] | = | 213
[13 empty] | T |  | 11118
Tower
| Beams | 4 | x | 25 | x | 2 | x | 2 | [5 empty] | = | 400
| Slab | 1 | x | 29 | x | 29 | x | 0.5 | [5 empty] | = | 421
| O.H.Tank Beams | 4 | x | 24 | x | 1 | x | 2 | [5 empty] | = | 192
| O.H.Base | 1 | x | 24 | x | 12 | x | 0.5 | [5 empty] | = | 144
| O.H Walls | 1 | x | 2 | x ( | 24 | + | 12 | ) x | 0.5 | x | 4.5 |  | = | 162
| O.H Slab | 1 | x | 28 | x | 16 | x | 0.42 | [5 empty] | = | 188
| U.G Base | 1 | x | 25 | x | 15 | x | 0.75 | [5 empty] | = | 281
| U.G Walls | 1 | x | 2 | x ( | 25 | + | 15 | ) x | 0.75 | x | 6 |  | = | 360
| U.G Top Slab | 1 | x | 28.5 | x | 18.5 | x | 0.5 | [5 empty] | = | 264
| P/Room Beams | 1 | x | 2 | x ( | 10 | + | 10 | ) x | 0.5 | x | 2 |  | = | 40
| " Slab | 1 | x | 12 | x | 12 | x | 0.42 | [5 empty] | = | 60
| S/case base | 1 | x | 2 | x | 8 | x | 3 | x | 3 |  |  |  | = | 144
| " Flights | 2 | x | 3 | x | 15 | x | 8 | x | 0.58 |  |  |  | = | 418
| " steps | 2 | x | 3 | x | 12 | x | 0.5 | x | 8 | x | 2 |  | = | 576
| " Landing | 1 | x | 2 | x | 24 | x | 10 | x | 0.5 |  |  |  | = | 240
| Labs. Table | 8 | x | 3 | x | 20 | x | 4 | x | 0.33 |  |  |  | = | 634
| Labs. Table | 8 | x | 2 | x | 30 | x | 3 | x | 0.33 |  |  |  | = | 475
| Anti Store slab | 1 | x | 16 | x ( | 15 | + | 10 | ) x | 3 | x | 0.33 |  | = | 396
| Anti Store slab | 1 | x | 2 | x ( | 10 | + | 15 | ) x | 3 | x | 0.33 |  | = | 50
| Window chajja | 1 | x | 70 | x | 8 | x | 2 | x | 0.33 |  |  |  | = | 370
| Vent Chajja | 1 | x | 2 | x ( | 34 | + | 39 | ) x | 2 | x | 0.33 |  | = | 96
[13 empty] | U |  | 5911
| Total:- |  | ( A+B+C+D+E+F+G+H+I+J+K+L+M+N+O+P+Q+R+S+T+U) | [10 empty] | = | 79387
7 | Fabrication of steel r/f for c.c in/c cutting bending laying in position making and fastening in/c cost of binding wire (also in/c removal of rust from bars)(S.I.No.7 (a & b)/P-20)
Qty same as item No: 6 |  | 79387
| TOR STEEL (60000 PSI) | 79387 |  |  | x | 7 | x | 0.9 |  | / | 112 |  |  | = | 4465.5188
| MILD STEEL (30000 PSI) | 79387 |  |  | x | 7 | x | 0.1 |  | / | 112 |  |  | = | 496.1687
8 | P/L 1:3:6 c.c solid block masonary wall 6"& above in thickness set in 1:6 c.m in G.F. Super structure in/c raking out joints & curing etc. complete. (S.I.No: 22/P-22)
A | Qnty same as item No.1 © | ( | 5801.32 |  | x | 0.67 | x | 8.25 | )/( | 2 | x | 2 | ) | = | 8017
| Grid 20 | 1 | x | 80 | x | 0.67 | x | 8.25 | [5 empty] | = | 442
| Grid '19' | 1 | x | 66.5 | x | 0.67 | x | 8.25 | [5 empty] | = | 368
| Grid 'N' | 1 | x | 44 | x | 0.67 | x | 8.25 | [5 empty] | = | 243
| Grid 2 to 10 | 5 | x | 25 | x | 0.67 | x | 8.25 | [5 empty] | = | 691
| Grid 'M' | 1 | x | 164 | x | 0.67 | x | 8.25 | [5 empty] | = | 907
| Grid 12,13 | 2 | x | 34 | x | 0.67 | x | 8.25 | [5 empty] | = | 376
| P/Room | 1 | x | 2 | x ( | 10 | + | 10 | ) x | 0.67 | x | 8.25 |  | = | 221
| Qnty same as item No.6 'H' |  | 461 |  | x | 8.25 | / | 2.5 | [5 empty] | = | 1521.3
| Qnty same as item No.6 'I' |  | 1707 |  | x | 8.25 | / | 2.5 | [5 empty] | = | 5633.1
| Qnty same as item No.6 'J' |  | 204 |  | x | 8.25 | / | 2.5 | [5 empty] | = | 673.2
[13 empty] | A |  | 19092.6
| Labs Tables | 8 | x | 3 | x | 6 | x | 3 | x | 0.67 | x | 3.5 |  | = | 1013
| Labs Tables | 8 | x | 2 | x | 8 | x | 3 | x | 0.67 | x | 3.5 |  | = | 900
| Ant / Store | 1 | x | 16 | x | 7 | x | 2 | x | 0.67 | x | 3.5 |  | = | 525
| kit: | 1 | x | 1 | x | 7 | x | 2 | x | 0.67 | x | 3.5 |  | = | 33
[13 empty] | B |  | 2471
F.floor
| C/R B/S L/W | 1 | x | 235.67 | x | 0.67 | x | 8.17 | [5 empty] | = | 1290
| C/R Mid L/W | 1 | x | 164 | x | 0.67 | x | 8.17 | [5 empty] | = | 898
| C/R F/S L/W | 1 | x | 164 | x | 0.67 | x | 8.17 | [5 empty] | = | 898
| Lav: P/walls | 4 | x | 5 | x | 0.67 | x | 8.17 | [5 empty] | = | 109
| Lav: P/walls | 1 | x | 25 | x | 0.67 | x | 8.17 | [5 empty] | = | 137
| Labs | 1 | x | 44.5 | x | 0.67 | x | 8.17 | [5 empty] | = | 244
| Lav: | 2 | x | 2 | x | 102.67 | x | 0.67 | x | 8.17 |  |  |  | = | 2248
| Anti / Store | 2 | x | 11.33 | x | 0.67 | x | 8.17 | [5 empty] | = | 124
| Labs | 4 | x | 10 | x | 0.67 | x | 8.17 | [5 empty] | = | 219
| Labs | 1 | x | 102.67 | x | 0.67 | x | 8.17 | [5 empty] | = | 562
| Lav: | 1 | x | 129 | x | 0.67 | x | 8.17 | [5 empty] | = | 706
| Lav: | 5 | x | 5 | x | 0.67 | x | 8.17 | [5 empty] | = | 137
| Lav: end walls | 1 | x | 30 | x | 0.67 | x | 8.17 | [5 empty] | = | 164
| C/Room P/Wall | 6 | x | 25 | x | 0.67 | x | 8.17 | [5 empty] | = | 821
| Lobby | 1 | x | 70 | x | 0.67 | x | 8.17 | [5 empty] | = | 383
| Labs | 11 | x | 30 | x | 0.67 | x | 8.17 | [5 empty] | = | 1806
[13 empty] | C |  | 10746
| Tower Walls | 4 | x | 24 | x | 0.67 | x | 8.17 | [5 empty] | = | 525
[13 empty] | D |  | 525
Deduction.
| Door D | 48 | x | 4 | x | 0.67 | x | 8 | [5 empty] | = | 1029
| Door D1 | 10 | x | 3.5 | x | 0.67 | x | 8 | [5 empty] | = | 188
| Door D2 | 21 | x | 3 | x | 0.67 | x | 8 | [5 empty] | = | 338
| Door D3 | 25 | x | 2.5 | x | 0.67 | x | 8 | [5 empty] | = | 335
| windows | 1 | x ( | 20 + 32 + 11 + 12 |  |  | ) x | 6 | x | 0.67 | x | 5 |  | = | 1508
| wind-1 | 1 | x ( | 3 + 5 | ) x | 4 | x | 0.67 | x | 5 |  |  |  | = | 107
| wind-2 | 1 | x ( | 1 + 1 | ) x | 2 | x | 0.67 | x | 5 |  |  |  | = | 13
| wind-3 | 1 | x ( | 6 + 6 | ) x | 8 | x | 0.67 | x | 5 |  |  |  | = | 322
| Vent | 1 | x | 28 | x | 3 | x | 0.67 | x | 1.5 |  |  |  | = | 84
| Vent - 2 | 1 | x | 28 | x | 5 | x | 0.67 | x | 1.5 |  |  |  | = | 141
[13 empty] | E |  | 4065
| Total :- |  | ( | A + B + C + D |  |  | ) - | E
|  |  |  | 32834.6 |  |  | - | 4065 | [5 empty] | = | 28769.6
9 | P/L 1:3:6 c.c solid block masonary wall 6" Below in thickness set in 1:6 c.m in G.F. Super structure I/c raking outjoints & curing etc, complete. (S.I.No: 23/P-22)
| Qnty same as item No.1 ( C ) | ( | 5801.32 |  | x | 0.5 | x | 3 | )/( | 2 | x | 2 | ) | = | 2175
| C/Wall | 1 | x | 1600 | x | 0.5 | x | 6 | [5 empty] | = | 4800
| Pillers | 1 | x | 176 | x | 1 | x | 0.5 | x | 6 |  |  |  | = | 528
7503
10 | P/F G.I. Frames / Chowkats of size 7"x2" or 4-1/2"x3" for windows using 20 gauge G.I. Sheet in/c welded hinges & fixing at site with necessary hold fasts, filling with cement sand slurry of ratio 1:6 & repairing the jambs. The cost also in/c all carriage tools & plants used in making and fixing. (S.I. No.28/P-98).
Door
| Door | 1 | x | 48 | x | 20 | [7 empty] | = | 960
| Door - 1 | 1 | x | 10 | x | 19.5 | [7 empty] | = | 195
| Door - 2 | 1 | x | 21 | x | 19 | [7 empty] | = | 399
| Door - 3 | 1 | x | 25 | x | 18.5 | [7 empty] | = | 463
2017
Windows
| Windows | 1 | x | 75 | x | 22 | [7 empty] | = | 1650
| Wondow -1 | 1 | x | 8 | x | 18 | [7 empty] | = | 144
| Wondow -2 | 1 | x | 2 | x | 14 | [7 empty] | = | 28
| Wondow -3 | 1 | x | 12 | x | 26 | [7 empty] | = | 312
| Vent- 1 | 1 | x | 28 | x | 9 | [7 empty] | = | 252
| Vent -2 | 1 | x | 28 | x | 13 | [7 empty] | = | 364
2750
11 | P/F in position doors & windows and vatilators of first class deodar wood frames and 13/4" thick commercial ply veneer shutters of first class deodar skelton (Hollow) and commercial ply wood (3 Ply) in/c fast hinges tower bolts etc & one Mortic lock and hooks(S.I.No.9/P-66). (Only Shutters)
| Door | 1 | x | 48 | x | 3.67 | x | 7.83 | [5 empty] | = | 1379
| Door - 1 | 1 | x | 10 | x | 3.12 | x | 7.83 | [5 empty] | = | 244
| Door - 2 | 1 | x | 21 | x | 2.67 | x | 7.83 | [5 empty] | = | 439
| Door - 3 | 1 | x | 25 | x | 2.17 | x | 7.83 | [5 empty] | = | 425
2487
12 | First class deodar wood wrought joinery in doors and windows fixed in position I/c chowkhats holds fasts hinges iron tower with hooks etc complete 1-3/4" thick (S.I.No.8-b/P-65) (Only Shutters)
| Windows | 1 | x | 75 | x | 5.67 | x | 4.67 | [5 empty] | = | 1986
| Wondow -1 | 1 | x | 8 | x | 3.67 | x | 4.67 | [5 empty] | = | 137
| Wondow -2 | 1 | x | 2 | x | 1.67 | x | 4.67 | [5 empty] | = | 16
| Wondow -3 | 1 | x | 12 | x | 7.67 | x | 4.67 | [5 empty] | = | 430
| Vent- 1 | 1 | x | 28 | x | 1.17 | x | 2.67 | [5 empty] | = | 87
| Vent -2 | 1 | x | 28 | x | 1.17 | x | 4.67 | [5 empty] | = | 153
2809
13 | Flooring of mosaic (marble chips) tiles of white cement laid flat in 1:2 grey cement mortor over 3/4" thick bed of grey cement mortor 1:2 (S.I.No.66/P-54)
| C/Rooms G.F + F.F | 1 | x | 10 | x | 30 | x | 25 | [5 empty] | = | 7500
| Ver G.F + F.F | 1 | x | 2 | x | 164 | x | 7 | [5 empty] | = | 2296
| Canteen / Kit | 1 | x | 30 | x | 30 | [7 empty] | = | 900
| Canteen / Kit | 1 | x | 10 | x | 15 | [7 empty] | = | 150
| Labs: | 2 | x | 4 | x | 30 | x | 40 | [5 empty] | = | 9600
| Stat: Lab | 1 | x | 25 | x | 30 | [7 empty] | = | 750
| Comm: Room | 1 | x | 30 | x | 25 | [7 empty] | = | 750
| Anti / Store | 2 | x | 8 | x | 10 | x | 15 | [5 empty] | = | 2400
| Ver: | 2 | x | 139 | x | 7 | [7 empty] | = | 1946
| Ver: | 2 | x | 129 | x | 7 | [7 empty] | = | 1806
| Guard Rooms | 1 | x | 2 | x | 14 | x | 14 | [5 empty] | = | 392
| P/Room | 1 | x | 10 | x | 10 | [7 empty] | = | 100
28590
14 | Flooring of mosaic (marble chips) tiles of white cement laid flat in 1:2 white cement mortor over 3/4" thick bed of grey cement mortor 1:2 (S,I,No.66 P-50)
| Admin Block | 1 | x | 66 | x | 84 | [7 empty] | = | 5544
| Ent: Lobby | 1 | x | 2 | x | 71 | x | 69 | [5 empty] | = | 9798
15342
15 | Vertical damp proof course 3/4" thick cement plaster 1:2 with bitumen a (20 lbs per %sft ) (S.I.No.100-p/103)
| Qnty same as item No.-1 'C' |  | 5801.32 |  | x | 3 | /( | 2 | x | 2 | ) |  |  |  | 4351
| Tank Bottom | 1 | x | 2 | x | 1600 | x | 2 | [5 empty] | = | 6400
| U.G.Tank I/s | 1 | x | 2 | x ( | 25 | + | 15 | ) x | 6.5 |  |  |  | = | 520
| U.G.Tank I/s | 1 | x | 2 | x ( | 24 | + | 12 | ) x | 4 |  |  |  | = | 288
11559
16 | P/F with sunkun iron screws wooden architrave approved design /shapemhaving width not less than 2-1/2 inches as directed by Engineer Incharge (S.I.No.60 P-73).
| Doors | 1 | x | 48 | x | 20 | [7 empty] | = | 960
| Door-1 | 1 | x | 10 | x | 19.5 | [7 empty] | = | 195
| Door-2 | 1 | x | 21 | x | 19 | [7 empty] | = | 399
| Door-3 | 1 | x | 25 | x | 18.5 | [7 empty] | = | 462.5
| Window | 1 | x | 75 | x | 22 | [7 empty] | = | 1650
| window-1 | 1 | x | 8 | x | 18 | [7 empty] | = | 144
| window-2 | 1 | x | 2 | x | 14 | [7 empty] | = | 28
| window-3 | 1 | x | 12 | x | 26 | [7 empty] | = | 312
| Vent-1 | 1 | x | 28 | x | 9 | [7 empty] | = | 252
| Vent-2 | 1 | x | 28 | x | 9 | [7 empty] | = | 252
4654.5
17 | Cement plaster 1:4 upto 20 height (c) 3/4" thick. (S.I.No.11 © /P-58)
| Qnty same as item No.8-A | ( | 19092.6 |  | x | 2 | x | 12.25 | )/( | 0.67 | x | 8.25 | ) | = | 84626
| Qnty same as item No.8-B | ( | 2471 |  | x | 2 | x | 3.83 | )/( | 0.67 | x | 3.5 | ) | = | 8072
| Qnty same as item No.8-C | ( | 10746 |  | x | 2 | x | 12.17 | )/( | 0.67 | x | 8.17 | ) | = | 47783
| Qnty same as item No.8-D | ( | 525 |  | x | 2 | x | 9.17 | )/( | 0.67 | x | 7.17 | ) | = | 2004
| Qnty same as item No.1-C | ( | 5801.32 |  | x | 2 | x | 3.25 | )/( | 2 | x | 2 | ) | = | 9427
| C/Wall | 1 | x | 2 | x | 1600 | x | 6.25 | [5 empty] | = | 20000
171912
18 | White wash three coats (S.I.No.26 ©/P-60).
| Qnty same as item No.6-R |  | 15830 |  | / | 0.5 | [7 empty] | = | 31660
| Qnty same as item No.6-T |  | 11118 |  | / | 0.5 | [7 empty] | = | 22236
| Tower Slab | 1 | x | 29 | x | 29 | [7 empty] | = | 841
| P/Room | 1 | x | 12 | x | 12 | [7 empty] | = | 144
| S/Case flight | 2 | x | 3 | x | 15 | x | 8 | [5 empty] | = | 720
| S/Case landing | 1 | x | 2 | x | 24 | x | 10 | [5 empty] | = | 480
| T-Beam | 20 | x | 30 | x | 2 | x | 2.5 | [5 empty] | = | 3000
| T-Beam | 10 | x | 2 | x | 25 | x | 2 | [5 empty] | = | 1000
60081
19 | Primary coat of chalk under distemper. (S.I.No. 23/C-9)
| Qnty same as item No.17 |  | 171912 | [10 empty] | = | 171912
20 | Distempering (c) 3 coats. (S.I.No. 24(c)/C-9)
| Qnty same as item No.19 |  | 171912 | [10 empty] | = | 171912
21 | Painting new surface, Painting doors and windows any type in/c edges, three coats (S.I.NO:5 © /P-77).
| Doors | 2 | x | 48 | x | 4 | x | 8 | [5 empty] | = | 3072
| Door-1 | 2 | x | 10 | x | 3.5 | x | 8 | [5 empty] | = | 560
| Door-2 | 2 | x | 21 | x | 3 | x | 8 | [5 empty] | = | 1008
| Door-3 | 2 | x | 25 | x | 2.5 | x | 8 | [5 empty] | = | 1000
| Window | 2 | x | 75 | x | 6 | x | 5 | [5 empty] | = | 4500
| window-1 | 2 | x | 8 | x | 4 | x | 5 | [5 empty] | = | 320
| window-2 | 2 | x | 2 | x | 2 | x | 5 | [5 empty] | = | 40
| window-3 | 2 | x | 12 | x | 8 | x | 5 | [5 empty] | = | 960
| Vent-1 | 2 | x | 28 | x | 3 | x | 1.5 | [5 empty] | = | 252
| Vent-2 | 2 | x | 28 | x | 5 | x | 1.5 | [5 empty] | = | 420
12132
22 | Masoic dado or skirting one part of white cement & 2 part of marble chips laid over 1/2" thick cement plaster 1:3 complete with finishing 3/8" thick (S.I.No.40/P-51).
| c/Room G.F + F.F | 10 | x | 2 | x ( | 30 | + | 25 | ) x | 0.5 |  |  |  | = | 550
| Ver: | 2 | x | 2 | x ( | 164 | + | 7 | ) x | 0.5 |  |  |  | = | 342
| Canteen / Kit: | 1 | x | 2 | x ( | 30 | + | 30 | ) x | 0.5 |  |  |  | = | 60
| Canteen / Kit: | 1 | x | 2 | x ( | 10 | + | 15 | ) x | 0.5 |  |  |  | = | 25
| Labs | 8 | x | 2 | x ( | 30 | + | 40 | ) x | 0.5 |  |  |  | = | 560
| Labs | 1 | x | 2 | x ( | 25 | + | 30 | ) x | 0.5 |  |  |  | = | 55
| Commn: Room | 1 | x | 2 | x ( | 25 | + | 30 | ) x | 0.5 |  |  |  | = | 55
| Anti / Store | 16 | x | 2 | x ( | 10 | + | 15 | ) x | 0.5 |  |  |  | = | 400
| Ver: | 2 | x | 2 | x ( | 139 | + | 7 | ) x | 0.5 |  |  |  | = | 292
| Ver: | 2 | x | 2 | x ( | 129 | + | 7 | ) x | 0.5 |  |  |  | = | 272
| G/Room | 2 | x | 2 | x ( | 14 | + | 14 | ) x | 0.5 |  |  |  | = | 56
| R/Room | 1 | x | 2 | x ( | 10 | + | 10 | ) x | 0.5 |  |  |  | = | 20
| window | 1 | x | 75 | x | 6 | x | 1.25 | [5 empty] | = | 562.5
| window | 1 | x | 8 | x | 4 | x | 1.25 | [5 empty] | = | 40
| window | 1 | x | 2 | x | 2 | x | 1.25 | [5 empty] | = | 5
| window | 1 | x | 12 | x | 8 | x | 1.25 | [5 empty] | = | 120
| Ver: Opening D/Walls Top | 1 | x | 34 | x | 9 | x | 1.25 | [5 empty] | = | 382.5
| Ver: Opening D/Walls Top | 1 | x | 18 | x | 9 | x | 1.25 | [5 empty] | = | 202.5
| Ver: Opening D/Walls Top | 1 | x | 32 | x | 9 | x | 1.25 | [5 empty] | = | 360
4359.5
23 | Mosaic dado or skirting one part of white cement and two part of marble chips laid over 1/2" thick plaster 1:3 complete with finishing 3/8" thick (S.I.No.40 P-47)
| Ent: lobby | 2 | x | 2 | x ( | 71 | + | 69 | ) x | 1 |  |  |  | = | 560
| Admin Block Lib: | 1 | x | 2 | x ( | 30 | + | 40 | ) x | 0.5 |  |  |  | = | 70
| Admin: off: | 2 | x | 2 | x ( | 18 | + | 14 | ) x | 0.5 |  |  |  | = | 64
| Admin: staff | 1 | x | 2 | x ( | 18 | + | 36 | ) x | 0.5 |  |  |  | = | 54
| Admin Union | 1 | x | 2 | x ( | 18 | + | 12 | ) x | 0.5 |  |  |  | = | 30
| Ver: | 1 | x | 2 | x ( | 85 | + | 10 | ) x | 0.5 |  |  |  | = | 95
| Ver: | 1 | x | 2 | x ( | 85 | + | 6 | ) x | 0.5 |  |  |  | = | 91
| Off: / reading | 1 | x | 2 | x ( | 13.33 | + | 10 | ) x | 0.5 |  |  |  | = | 23.33
| Off: / reading | 1 | x | 2 | x ( | 16 | + | 10 | ) x | 0.5 |  |  |  | = | 26
| Major | 1 | x | 2 | x ( | 16 | + | 16 | ) x | 0.5 |  |  |  | = | 32
| Liver | 1 | x | 2 | x ( | 7.67 | + | 16 | ) x | 0.5 |  |  |  | = | 23.67
| Store | 1 | x | 2 | x ( | 13.33 | + | 7.75 | ) x | 0.5 |  |  |  | = | 21.08
| Dispensory | 1 | x | 2 | x ( | 16 | + | 16 | ) x | 0.5 |  |  |  | = | 32
1122.08
24 | Laying white marble flooring fine dressed on the surface without winding set un lime mortor 1:2 in/c rubbing and polishing of the joints 1" thick flooring (S.I.No.28-b/P-49).
| S/Case steps Hostel | 2 | x | 3 | x | 12 | x | 8 | x | 1 |  |  |  | = | 576
| Landing | 2 | x | 24 | x | 10 | [7 empty] | = | 480
| counter | 1 | x | 12 | x | 6 | [7 empty] | = | 72
1128
25 | P/F 3/8" thick marble tiles of approved quality and colour and shade size 8"x 4" / 6" x4" in dado skirting and facing removal tucking of existing plaster surface etc 1/2" thick base of cement mortor 1:3 setting of tiles in slurry of white cement over mortor base in/c finishing , cleaning and polishing etc complete for new work (S.I.No.68-i / P-55)
| S/Case Landing | 2 | x ( | 10 | + | 24 | + | 10 | ) x | 3 |  |  |  | = | 264
| S/Case flight | 2 | x | 2 | x | 15 | x | 3 | [5 empty] | = | 180
444
26 | M/F grating in opening in/c 1/16" thick sheeting in/c angle iron frame 2"x2"x3/8" and 3/4" square bars 4" centre to centre with locking arrangement (S.I.No.29 P-91).
| S/Case sides | 2 | x | 4 | x | 15 | x | 3 | [5 empty] | = | 360
360
27 | Hard wood railing of any shape & size design I/c bends & corners fixed in position I/c polishing complete.as directed Shisham wood (S.I.No.30 P-62).
| S/Case sides | 1 | x | 2 | x | 4 | x | 15 | [5 empty] | = | 120
120
28 | M/F steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"3/8" and 3/4" square bar 4" C/C with locking arragement (S.I.No.24/P-97)
| M.Gate | 1 | x | 2 | x | 4 | x | 7 | [5 empty] | = | 56
| M.Gate | 1 | x | 1 | x | 12 | x | 7 | [5 empty] | = | 84
140
29 | Painting new surface, painting guard bars gates of iron bars grating railing in/c standard brasses etc and similar open work three coats (S.I.No.5 (d)/P-77).
| S/Case side | 2 | x | 4 | x | 15 | x | 3 | [5 empty] | = | 360
| M.Gates | 2 | x | 2 | x | 4 | x | 7 | [5 empty] | = | 112
| M.Gates | 1 | x | 2 | x | 12 | x | 7 | [5 empty] | = | 168
640
30 | Making notice board made with cement sand ( S.I.No.1 P/89)
| C/Room | 1 | x | 10 | x | 12 | x | 4 | [5 empty] | = | 480
| Labs | 1 | x | 8 | x | 15 | x | 4 | [5 empty] | = | 480
960
31 | Reinforcement Cement Concrete Spout (S.I.No.13 P-21 ).
| Spouts | 1 | x | 30 | [9 empty] | = | 30
32 | Providing and laying topping cement concrete 1:2:4 including surface finishing and dividing into panells 2" thick. (S.I.No. 16 (b) / P-47)
| Qnty same as item No. 6-T |  | 11118 |  | / | 0.5 | [7 empty] | = | 22236
| Roof statis: lab | 1 | x | 25 | x | 39 | [7 empty] | = | 975
| Canteen roof | 1 | x | 34.33 | x | 33.67 | [7 empty] | = | 1155.89
| Canteen roof | 1 | x | 22.33 | x | 13.67 | [7 empty] | = | 305.25
| Commn: room | 1 | x | 45 | x | 28.67 | [7 empty] | = | 1290.15
| Admin Roof | 1 | x | 88.5 | x | 73.33 | [7 empty] | = | 6489.71
| O.H Base + Top | 1 | x | 29 | x | 29 | [7 empty] | = | 841
| U.G Base Top | 24 | x | 12 | x | 2 | [7 empty] | = | 576
| U.G Base Top | 1 | x | 25 | x | 15 | [7 empty] | = | 375
| P/Room | 1 | x | 12 | x | 12 | [7 empty] | = | 144
| G/ Room | 2 | x | 17.33 | x | 17.33 | [7 empty] | = | 600.66
| Lav: | 1 | x | 10.33 | x | 10.33 | [7 empty] | = | 106.71
35095.37
33 | Two coat of bitumen laid hot using 34lbs for % sft over roof blinded with sand at one part cft per sft (S.I.No.13 / P-41).
| Qnty same as item No. 32 |  | 35095.37 | [10 empty] | = | 35095.37
34 | Providing and laying topping cement concrete 1:2:4 including surface finishing and dividing into panells 3" thick. (S.I.No. 16 © / P-47)
| Canteen Kit | 1 | x | 30 | x | 30 | [7 empty] | = | 900
| Canteen Kit | 1 | x | 10 | x | 15 | [7 empty] | = | 150
| F/S Porch | 1 | x | 46 | x | 12 | [7 empty] | = | 552
| M/Gate sides | 1 | x | 32 | x | 20 | [7 empty] | = | 640
2242
35 | Supplying and fixing in position iron/steel grill of 3/4"x1/4" size flate iron of approved design in/c painting 3 coats etc complete (wt. not to be less than 3.7 lbs/Sft of finished grill) (S.I.No.26/P-97)
| Windows | 1 | x | 75 | x | 5.67 | x | 4.67 | [5 empty] | = | 1985.92
| Windows | 1 | x | 8 | x | 3.67 | x | 4.67 | [5 empty] | = | 137.11
| Windows | 1 | x | 2 | x | 1.67 | x | 4.67 | [5 empty] | = | 15.6
| Windows | 1 | x | 12 | x | 7.67 | x | 4.67 | [5 empty] | = | 429.83
| Vent | 1 | x | 28 | x | 1.17 | x | 2.67 | [5 empty] | = | 87.47
| Vent | 1 | x | 28 | x | 1.17 | x | 4.67 | [5 empty] | = | 152.99
2808.92
36 | P/F ornamental cement Jali 2" thick (1:2:4) without steel (S.I.No.10 P-20)
| Openings | 6 | x | 7 | x | 8.25 | [7 empty] | = | 346.5
| Tower | 1 | x | 24 | x | 8.25 | [7 empty] | = | 198
544.5
37 | Errection & removal of vertical centering for R.C.C plain or cement concrete work of Partal wood (2nd class) (S.I.No.18-b/P-21).
| D/Coloumn C-1 | 1 | x | 109 | x | 5.33 | x | 2.5 | [5 empty] | = | 1452.43
| D/Coloumn C-2 | 1 | x | 58 | x | 4 | x | 2.5 | [5 empty] | = | 580
| D/Coloumn C-3 | 1 | x | 26 | x | 6.5 | x | 2.5 | [5 empty] | = | 422.5
2454.93
38 | Cement concerete plain in/c placing compacting finishing curing complete & screening & washing of stone aggregate without shuttering ratio 1:3:6 (S.I.No.5-h P-18).
| D/Col: C-1 | 1 | x | 109 | x | 0.67 | x | 2 | x | 2.5 |  |  |  | = | 365.15
| D/Col: C-2 | 1 | x | 58 | x | 1 | x | 1 | x | 2.5 |  |  |  | = | 145
| D/Col: C-3 | 1 | x | 26 | x | 1 | x | 2.25 | x | 2.5 |  |  |  | = | 146.25
656.4
39 | Extra labour for laying concrete plain or reinforced 20'-40' height. (S.I.No.11-a P-21)
| Qnty same as item No.6-S |  | 5153 | [10 empty] | = | 5153
| Qnty same as item No.6-T |  | 11118 | [10 empty] | = | 11118
| Qnty same as item No.8-C |  | 10746 |  | x | 3 | / | 8.17 | [5 empty] | = | 3945.8996
| Qnty same as item No.38 |  | 656.4 | [10 empty] | = | 656.4
20873.2996
40 | Extra labour for Cement plaster (S.I.No.1 P-52 Remarks)
| Qnty same as item No.17 |  | 171912 |  | / | 3 | [7 empty] | = | 57304
41 | Extra labour for each storey above ground for mosaic conglomerate or tiles stone and wooden floor. (S.I.No.18 P-44)
| Qnty same as item No.13. |  | 28590 |  | / | 2 | [7 empty] | = | 14295
| Qnty same as item No.32 |  | 35095.37 | [10 empty] | = | 35095.37
49390.37
42 | Laying floor of aproved coloured glazed tile 1/4" thick in white cement 1:2 over 3/4" thick pigment cement mortor 1:2 complete (S.I.No.25 / P-49).
| Pricipal lav: | 1 | x | 18 | x | 5.5 | [7 empty] | = | 99
43 | Glazed tiles dado 1/4" thick laid in pigment over 1:2 cement sand mortar 3/4" thick in/c finishing (S.I.No.37/P-50)
| Pricipal lav: | 2 | x | 18 | x | 7 | [7 empty] | = | 252
| Pricipal lav: | 2 | x | 5.5 | x | 7 | [7 empty] | = | 77
329
44 | S/F in position Aluminium channels framing for hinged doors or Alcop made with 5mm thick tinted glass glazing (Belgium) and Alpha (Japan) locks I/c handles stoppers etc b) Deluxe model (Bronze) (S.I.No.113 P-104)
| Main Ent: | 2 | x | 12 | x | 8 | [7 empty] | = | 192
45 | S/F in position Aluminium channels framing for hinged slidding windows & ventilators of Alcop made with 5mm thick tinted glass glazing (Belgium) and Alpha (Japan) locks I/c handles stoppers etc complete b) Deluxe model (Bronze) (S.I.No.114 P-104)
| Windows (Main Ent:) | 3 | x | 6 | x | 5 | [7 empty] | = | 90
46 | Difference of S.R Cement (R.A approved)
| Qnty same as item No.6A |  | 6664 |  | x | 17.6 | % | [6 empty] | = | 1172.864
| Qnty same as item No.6C |  | 12808 |  | x | 17.6 | % | [7 empty] | 2254.208
3427.072

## BOQ
Bill of Quantity
STRENGTHENING PARTICIPATORY ORGANIZATION
1.REPAIR WORK GBPS SONHARO BHATTI KAMBAR SEMIS CODE:427070177
Sr. No | Description of Items | No. | x | L | x | W | x | D/H | = | Quantity
1 | Grouting
i | Removal of exisiting grout and Providing and laying of Cement mortar 1.5" thick grouting on classrooms,office and wrinda roof. | 2 | X | 20 | x | 16 | x |  | = | 640
|  | 1 | x | 41 | x | 7 | x |  | = | 287
2 | Plaster work
i | Removal of demage palster and Replastring (PATCHING) of demaged plaster work of (1:4) C/S of classrooms,wiranda and boundary wall upto Plinth level | 1 | x | 349 | x |  | x | 2 | = | 698
3 | Flooring
i | Removal of existing demage C.C block and Provinding and laying of pucca floor (1:2:4 ) in wiranda | 2 | x | 20 | x | 16 | x |  | = | 320
|  | 1 | x | 41 | x | 7 | x |  | = | 287
4 | Wooden work
i | Providing and fixing wooden door with frame | 1 | x |  |  | 3.5 | x | 7 | = | 24.5
5 | Solar System
i | Installation solar system 2pannel of 180 and 4 GFC fans with complete fitting | 2 | x
6 | Paint Work
i | Applying distembering ,oil paint Weather resistant paint coating such as ICI weather sheet sheild ,Berger weather coat or equivalent to exterior and interior walls or ceiling door windows including supplying all materials ,lobour scaffolding and removel and removel of debris etc with scoffoldings.(Class rooms, wiranda, boundary wall white wash inside and outside. | 1 | x |  | x |  | x |  | =
7 | Washroom repair
i | Rehabilitation of existing of toilet providing New WC and new CC block each with proper drainage and construction of proper spectic/mainhole | 2 | x | 5 | x | 4 | X |  | = | 40
ii | Providing water facility(including boring if needed) | 1 | x | [6 empty] | lumsum
8 | Steel Name Plate
i | Providing and fixing of steel name plate on front wall of school | 1 | x |  |  | 4 | x | 2 | x | 8
9 | Miscellaneous ( Paint work drawing of UNICEF LOGO and other art work) | 1 | x |  | x |  | x |  | =
9
10
11
12
13
14
15
16
17
18
19 | [10 empty] | TOTAL | 0
20
21
22
23
24
25
0